## Sheet1
Week – Task Module	Implementable Features	Detailed Activities	App Dev (man-day)	Date of activity
1 – Requirement understanding and configuring development pre requisites	1.1 Planning	1.1.1 Analyze the purpose, scope & objectives. / 1.1.2 Plan project schedule, WBS, SRS and delivery plan	3 / 5	07/03/22
		1.1.3 Understand product perspective, functionalities & constraints	8	07/04/22
	1.2 Gathering Requirements	1.2.1 Configure functional & non-functional requirements, dependencies & stakeholders	4 / 4	07/05/22
	1.3 Preparing Documentations	1.3.1 Prepare Use Case Diagram, Entity Relationship Diagram, Activity Diagram and Class Diagram.	2 / 4 / 2	07/06/22
		1.3.2 Complete SRS & WBS and submit.	8	07/07/22
2 – Backend design & development with API analysis	2.1 Configure API structure	2.1.1 List down the APIs and their usages	8	07/10/22
	2.2 Design Database	2.2.2 Design the database and the fields	8	07/11/22
		2.2.3 Design the relationships between databases	8	07/12/22
	2.3 Implement Backend	2.3.1 Start coding and implement the databases	8	07/13/22
		2.3.2 Complete backend and expose active APIs	8	07/14/22
3 – Frontend design and development	3.1 Design Frontend	3.1.1 Design the basic frontend with proper button & input fields	8	07/17/22
	3.2 Configure frontend with backend API	3.2.1 Plan how to connect and fetch data from the backend APIs	8	07/18/22
		3.2.2 Plan how to accept data in frontend and send to the backend	8	07/19/22
	3.3 Implement frontend & connect with backend	3.3.1 Start coding the frontend and complete the outlook design	8	07/20/22
		3.3.2 Connect the backend APIs and complete the data sending & receiving tasks.	8	07/21/22
4 – Testing project and submission	4.1 Project Testing	4.1.1 Develop test cases, conduct system testing & user acceptance testing	8	07/24/22
	4.2 Project Submission & Closing	4.2.1 Prepare presentation based on the complete project	8	07/25/22
		4.2.2 Final check to the deployment checklist and submit the project	8	07/26/22
			120