## Details_break_down(WBS)
Project Name | Trainee Management System
Project Stackholder | BJIT Academy
Date | 2023-01-07
Version | 1
WORk BREAKDOWN STRUCTURE of Trainee Management System (TMS)
# | Task Module | Features To be implemented | Activities to be done | Duration(hours) | Start Date | Task Status | End Date | Module Total (man-month) | Notes
Week 1 | 1.0 Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-01-07 | Complete | 2023-01-07
|  |  | 1.1.2 Develop project schedule | 2 | 2023-01-07 | Complete | 2023-01-07
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-02-07 | Complete | 2023-02-07
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-02-07 | Complete | 2023-02-07
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-02-07 | Complete | 2023-02-07
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-03-07 | Complete | 2023-03-07
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-04-07 | Complete | 2023-04-07
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-05-07 | Complete | 2023-05-07
|  |  | 1.3.2 Prepare UML DFD diagram | 4 | 2023-05-07 | Complete | 2023-05-07
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-06-07 | Complete | 2023-06-07
|  |  | 1.3.4 Prepare UML Activity diagram | 4 | 2023-07-07 | Complete | 2023-07-07
|  |  | 1.3.5 Prepare UML Sequence diagram | 4 | 2023-07-07 | Complete | 2023-07-07
Week 2 | 2.0 API Analysis and System Design
|  | 2.1 Analyze API structures and Endpoints | 2.1.1 Identify and analyze API endpoints related to Admin | 2 | 2023-08-07 | In Progress | 2023-08-07 |  | Need help from the ED to complete this section
|  |  | 2.1.2 Identify and analyze API endpoints related to Traineer | 2 | 2023-08-07 | Incomplete | 2023-08-07
|  |  | 2.1.3 Identify and analyze API endpoint related to Trainee | 2 | 2023-08-07 | Incomplete | 2023-08-07
|  |  | 2.1.4 Identify and analyze common API endpoints like login | 2 | 2023-08-07 | Incomplete | 2023-08-07
|  | 2.2 Document Endpiont Details | 2.2.1 Provide a description of each API endpoint, including its purpose and usage. | 2 | 2023-09-07 | Incomplete | 2023-09-07
|  |  | 2.2.2 Document the expected inputs and output | 4 | 2023-09-07 | Incomplete | 2023-09-07
|  | 2.3 Generate API Documentation | 2.3.1 Use documentation tool to generate API documentation. | 2 | 2023-09-07 | Incomplete | 2023-09-07
|  |  | 2.3.2 Include the defined request and response structures for each endpoint. | 2 | 2023-09-07 | Incomplete | 2023-09-07
|  |  | 2.3.3. Provide sample API requests and responses to demonstrate usage | 2 | 2023-10-07 | Incomplete | 2023-10-07
|  | 2.4 Design User Interface (UI) | 2.4.1 Design Dashborad for Admin, Traineer and Trainee | 6 | 2023-10-07 | Incomplete | 2023-10-07
|  |  | 2.4.2 Design left Sidebar Feature | 2 | 2023-10-07 | Incomplete | 2023-11-07
|  |  | 2.4.3 Design Batch, Course, Schedule etc Management feature for admin | 8 | 2023-11-07 | Incomplete | 2023-12-07
|  |  | 2.2.4 Design Assignement and Classroom Feature for Trainner | 4 | 2023-12-07 | Incomplete | 13/7/2023
|  |  | 2.4.5 Design Task Submission and Classroom Feature for Trainee | 4 | 13/7/2023 | Incomplete | 13/7/2023
|  | 2.5 Design database | 2.5.1 Identifying database entities | 4 | 14/7/2023 | Incomplete | 14/7/2023
|  |  | 2.5.2 Analyze relationship between entities | 4 | 14/7/2023 | Incomplete | 14/7/2023
Week 3 | 3.0 Development of Frontend & Backend Functionality
|  | 3.1 Implement trainer and trainee registration functionality | 3.1.1 Create registration forms for trainers and trainees | 2 | 15/7/2023 | Incomplete | 15/7/2023
|  |  | 3.1.2 Implement validation for registration fields | 2 | 15/7/2023 | Incomplete | 15/7/2023
|  |  | 3.1.3 Store registration data in the database | 2 | 15/7/2023 | Incomplete | 15/7/2023
|  | 3.2 Implement batch creation functionality | 3.2.1 Design a form to create batch with necessary fields | 1 | 15/7/2023 | Incomplete | 15/7/2023
|  | c | 3.2.2 Implement batch creation and storage in the database | 1 | 15/7/2023 | Incomplete | 15/7/2023
|  | 3.3 Implement course creation and assignment functionality | 3.3.1 Design a form to create courses with relevant details | 2 | 16/7/2023 | Incomplete | 16/7/2023
|  |  | 3.3.2 Allow admins to assign trainers to specific courses | 2 | 16/7/2023 | Incomplete | 16/7/2023
|  |  | 3.3.3 Store course and trainer assignments in the database | 4 | 17/7/2023 | Incomplete | 17/7/2023
|  | 3.4 Implement trainer and trainee assignment to batches | 3.4.1 Develop dynamic UI to assign multiple trainees to a batch | 2 | 17/7/2023 | Incomplete | 17/7/2023 |  | might need to do a meeting with frontend engineer
|  |  | 3.4.2 Allow admins to assign trainers and store in databse | 2 | 17/7/2023 | Incomplete | 17/7/2023
|  | 3.5 Develop batch scheduling functionality | 3.5.1 Design a scheduler interface for scheduling | 2 | 18/7/2023 | Incomplete | 18/7/2023
|  |  | 3.5.2 Allow admins to create and assign training programs | 2 | 18/7/2023 | Incomplete | 18/7/2023
|  |  | 3.4.3 Store batch schedules and training programs in the db | 2 | 18/7/2023 | Incomplete | 18/7/2023
| c | 3.6 Implement assignment and daily task creation functionality | 3.6.1 Provide a form for trainers to create assignments and daily tasks | 2 | 18/7/2023 | Incomplete | 18/7/2023
|  |  | 3.6.2 Enable assignment/task assignment to specific batches | 4 | 19/7/2023 | Incomplete | 19/7/2023
|  |  | 3.6.3 Store assignment and task data in the database | 2 | 19/7/2023 | Incomplete | 19/7/2023
|  | 3.7 Implement classroom features | 3.7.1 Develop a dashboard for trainers and trainees to access the classroom | 2 | 19/7/2023 | Incomplete | 19/7/2023
|  |  | 3.7.2 Implement Notice Board, post,comment functionality | 2 | 19/7/2023 | Incomplete | 19/7/2023
|  |  | 3.7.3 Store Assignment, post, comment in the database | 2 | 20/7/2023 | Incomplete | 20/7/2023
|  | 3.8 Enable assignment submission functionality | 3.8.1 Design a form for trainees to submit assignments in various file formats | 2 | 20/7/2023 | Incomplete | 20/7/2023
|  |  | 3.8.2 Provide a submission view for trainers to review and assess assignments | 4 | 20/7/2023 | Incomplete | 20/7/2023
|  |  | 3.8.3 Store assignment submission in the database | 2 | 20/7/2023 | Incomplete | 20/7/2023
|  | 3.9 Implement group chat feature | 3..9.1 Create a group chat interface for participants of a specific batch | 2 | 20/7/2023 | Incomplete | 20/7/2023
|  |  | 3.9.2 Enable textual communication among participants | 4 | 21/7/2023 | Incomplete | 21/7/2023
|  |  | 3.9.3 Allow sharing of images and files in the group chat | 4 | 21/7/2023 | Incomplete | 21/7/2023
Week 4 | 4.0 Quality Assurance and Project
|  | 4.1 App testing and quality assurance | 4.1.1 Implement Unit testing | 4 | 21/7/2023 | Incomplete | 21/7/2023
|  |  | 4.1.2 Conduct system testing | 2 | 21/7/2023 | Incomplete | 21/7/2023
|  |  | 4.1.3 Conduct User Acceptance Testing (UAT) | 8 | 22/7/2023 | Incomplete | 22/7/2023
| c |  | 4.1.4 Fix bugs and defects | 2 | 22/7/2023 | Incomplete | 22/7/2023
|  | 4.2 Prepare TMS project Presentation | 4.2.1 Make PPT for Presentation | 2 | 22/7/2023 | Incomplete | 22/7/2023
|  |  | 4.2.2 Go through all the project for Demostration | 4 | 22/7/2023 | Incomplete | 22/7/2023
|  | 4.3 Ready Source Code and Dockerize | 4.3.1 Push to Private Git Repository | 2 | 23/7/2023 | Incomplete | 23/7/2023
|  |  | 4.3.2 Create a Readme File | 3 | 23/7/2023 | Incomplete | 23/7/2023
| c |  | 4.3.2 Dockerize the Project | 1 | 23/7/2023 | Incomplete | 23/7/2023
|  | 4.4 Project closing | 4.4.1 Revise the project deployment checklist | 4 | 24/7/2023 | Incomplete | 24/7/2023
|  |  | 4.4.2 Deploy the application | 4 | 24/7/2023 | Incomplete | 24/7/2023
190