## Details_break_down(WBS)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date | End Date | Module Total (man-month)
Week 1
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-03-07 | 2023-08-07
|  |  | 1.1.2 Develop project schedule | 2 | 2023-03-07 | 2023-08-07
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-03-07 | 2023-08-07
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-03-07 | 2023-08-07
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-03-07 | 2023-08-07
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-03-07 | 2023-08-07
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-03-07 | 2023-08-07
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-03-07 | 2023-08-07
|  |  | 1.3.2 Prepare UML DFD diagram | 4 | 2023-03-07 | 2023-08-07
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-03-07 | 2023-08-07
|  |  | 1.3.4 Prepare UML Activity diagram | 2 | 2023-03-07 | 2023-08-07
|  |  | 1.3.5 Prepare UML Class diagram | 4 | 2023-03-07 | 2023-08-07
2 | Backend Development
|  | 2.1 Set up project and infrastructure | 2.1.1 Configure Database | 2 | 2023-10-07 | 16/7/2023
|  |  | 2.1.2 Create Models | 2 | 2023-10-07 | 16/7/2023
|  |  | 2.1.3 Create Controllers | 2 | 2023-10-07 | 16/7/2023
|  |  | 2.1.4 Create Services | 2 | 2023-10-07 | 16/7/2023
|  |  |  | 2 | 2023-10-07 | 16/7/2023
|  |  |  | 4 | 2023-10-07 | 16/7/2023
|  | 2.2 Develop Functional requirements | 2.2.1 Design Data save functionality | 8 | 2023-10-07 | 16/7/2023
|  |  | 2.2.2 Design Data information page | 4 | 2023-10-07 | 16/7/2023
|  |  | 2.2.3 Design update mechanism | 8 | 2023-10-07 | 16/7/2023
|  |  | 2.2.4 Design response to show on dashboard | 4 | 2023-10-07 | 16/7/2023
|  |  | 2.2.5 Identify intermediate data transfer mechanism | 4 | 2023-10-07 | 16/7/2023
|  | 2.3 Design database | 2.3.1 Identifying database entities | 8 | 2023-10-07 | 16/7/2023
|  |  | 2.3.2 Analyze relationship between entities | 8 | 2023-10-07 | 16/7/2023
3 | Frontend Development
|  | 3.1 Design UI pages | 3.1.1 Create pages for different features | 2 | 16/7/2023 | 21/7/2023
|  |  | 3.1.2 Design modals, and other in page components | 2 | 16/7/2023 | 21/7/2023
|  |  |  | 2 | 16/7/2023 | 21/7/2023
|  | 3.2 Develop frontend functionality | 3.2.1 Design dashboards | 2 | 16/7/2023 | 21/7/2023
|  | c | 3.2.2 Show information on dashboard based on login credentials | 2 | 16/7/2023 | 21/7/2023
|  |  | 3.2.3 Show batch information | 2 | 16/7/2023 | 21/7/2023
|  |  | 3.2.4 Show batch-wise assignments | 2 | 16/7/2023 | 21/7/2023
|  |  | 3.2.5 Show date-wise schedules | 2 | 16/7/2023 | 21/7/2023
|  |  | 3.2.6 Show trainer wise courses | 2 | 16/7/2023 | 21/7/2023
|  |  | 3.2.7 Show trainees in a box. | 2 | 16/7/2023 | 21/7/2023
|  |  | 3.2.8 Show trainers in a box. | 2 | 16/7/2023 | 21/7/2023
c |  |  | 3.2.9 Show schedules based on credentials | 2 | 16/7/2023 | 21/7/2023
|  |  | 3.2.10 Implement classroom modules | 2 | 16/7/2023 | 21/7/2023
| c |  | 3.2.11 Show classroom informations and implement search functionality | 4 | 16/7/2023 | 21/7/2023
|  |  | 3.2.12 Show group chats, chat history, chat interface | 4 | 21/7/2023 | 21/7/2023
4 | Quality Assurance and Project closing
| c | 4.1 App testing and quality assurance | 4.1.1 Develop test cases | 8 | 22/7/2023 | 23/7/2023
|  |  | 4.1.2 Conduct system testing | 4 | 22/7/2023 | 23/7/2023
|  |  | 4.1.3 Conduct User Acceptance Testing (UAT) | 8 | 22/7/2023 | 23/7/2023
| c |  | 4.1.4 Fix bugs and defects | 2 | 22/7/2023 | 23/7/2023
|  | 4.2 Project closing | 4.2.1 Revise the project deployment checklist | 4 | 22/7/2023 | 23/7/2023
|  |  | 4.2.2 Deploy the application | 4 | 22/7/2023 | 23/7/2023
2
164