## Details_break_down(WBS)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date | End Date | Module Total (man-month)
Week 1
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-03-07 | 2023-03-07
|  |  | 1.1.2 Develop project schedule | 2 | 2023-03-07 | 2023-03-07
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-03-07 | 2023-03-07
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-04-07 | 2023-04-07
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-04-07 | 2023-04-07
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-05-07 | 2023-05-07
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-06-07 | 2023-06-07
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-06-07 | 2023-06-07
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-06-07 | 2023-07-07
|  |  | 1.3.4 Prepare UML Activity diagram | 2 | 2023-07-07 | 2023-07-07
2 | API Analysis and System Design
|  | 2.1 Set up project and infrastructure | 2.1.1 Configure Database | 2 | 2023-08-07 | 2023-08-07
|  |  | 2.1.2 Create Models | 2 | 2023-08-07 | 2023-08-07
|  |  | 2.1.3 Create Controllers | 2 | 2023-08-07 | 2023-08-07
|  |  | 2.1.4 Create Services | 2 | 2023-08-07 | 2023-08-07
|  | 2.2 Design User Interface (UI) | 2.2.1 Design Login page | 8 | 2023-09-07 | 2023-09-07
|  |  | 2.2.2 Design Register page | 4 | 2023-10-02 | 2023-10-02
|  |  | 2.2.3 Design dashboard | 8 | 2023-11-02 | 2023-11-02
|  |  | 2.2.4 Design classroom page | 8 | 2023-12-02 | 2023-12-02
|  |  | 2.2.5 Design trainee and trainer profile page | 4 | 13/2/2023 | 13/2/2023
|  | 2.3 Design database | 2.3.1 Identifying database entities | 8 | 14/2/2023 | 14/2/2023
|  |  | 2.3.2 Analyze relationship between entities | 8 | 15/2/2023 | 15/2/2023
3 | Development
|  | 3.1 Login/ Registration | 3.1.1 Admin register Trainee and trainers | 2 | 16/2/2023 | 16/2/2023
|  |  | 3.1.2 Trainer and trainee can login and update their information | 2 | 16/2/2023 | 16/2/2023
|  |  | 3.1.3 Trainer and trainee can update their information | 2 | 16/2/2023 | 16/2/2023
|  | 3.2 Create Batches | 3.2.1 admin can create batch | 2 | 16/2/2023 | 16/2/2023
|  | c | 3.2.2 admin can updaet batch details | 2 | 17/2/2023 | 17/2/2023
|  | 3.3 Create Courses | 3.3.1 admin can create course | 2 | 17/2/2023 | 17/2/2023
|  |  | 3.3.2 admin can see all the course | 2 | 17/2/2023 | 17/2/2023
|  |  | 3.3.3 admin can update and delete course | 2 | 17/2/2023 | 17/2/2023
|  | 3.4 Assign Trainees to Batches | 3.4.1 admin can assign trainee to batch | 2 | 18/2/2023 | 18/2/2023
|  |  | 3.4.2 admin can remove trainee to batch | 2 | 18/2/2023 | 18/2/2023
|  | 3.5 Batch Scheduling | 3.5.1 admin can assign course with proper batch scheduling | 2 | 18/2/2023 | 18/2/2023
|  |  | 3.5.2 admin can delete scheduling and update | 2 | 18/2/2023 | 18/2/2023
|  | 3.6 Assignment creation | 3.6.1 trainer can create assignment | 2 | 19/2/2023 | 19/2/2023
|  |  | 3.6.2 trainer can update and delete assignmet | 2 | 19/2/2023 | 19/2/2023
|  |  | 3.6.3 trainer can can see all the assignment | 2 | 19/2/2023 | 19/2/2023
|  | 3.7 Classroom features with a dashboard, notice board | 3.7.1 trainer can post assignment | 2 | 19/2/2023 | 19/2/2023
|  |  | 3.7.2 trainer can post any type of file | 2 | 20/2/2023 | 20/2/2023
|  |  | 3.7.3 trainer can give notice board message | 2 | 20/2/2023 | 20/2/2023
c |  |  | 3.7.4 trainee can give comment upder trainer post | 2 | 20/2/2023 | 20/2/2023
|  | 3.8 Submit the assignments | 3.8.1 trainee can submit assignment | 2 | 20/2/2023 | 20/2/2023
|  |  | 3.8.2 trainer can see all the assignmet | 2 | 21/2/2023 | 21/2/2023
4 |  | 3.9 Group chat feature | 3.9.1 trainee can communicate themself groupchat | 2 | 21/2/2023 | 21/2/2023
|  |  | 3.9.2 trainee can send any formate of file | 2 | 21/2/2023 | 21/2/2023
c
Quality Assurance and Project closing
| c | 4.1 App testing and quality assurance | 4.1.1 Develop test cases | 8 | 22/7/2023 | 22/7/2023
|  |  | 4.1.2 Conduct system testing | 4 | 23/7/2023 | 23/7/2023
|  |  | 4.1.3 Conduct User Acceptance Testing (UAT) | 8 | 23/7/2023 | 24/7/2023
| c |  | 4.1.4 Fix bugs and defects | 2 | 24/7/2023 | 24/7/2023
|  | 4.2 Project closing | 4.2.1 Revise the project deployment checklist | 4 | 24/7/2023 | 24/7/2023
|  |  | 4.2.2 Deploy the application | 4 | 25/7/2023 | 25/7/2023
2
166