## wrb (2)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date | End Date | Module Total (man-month) | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15
1.0 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2/2/2023 | 2/2/2023
|  |  | 1.1.2 Develop project schedule | 2 | 2/2/2023 | 2/2/2023
|  |  | 1.1.3 Develop a delivery plan | 2 | 2/2/2023 | 2/2/2023
|  | 1.2 Requirements Gathering | 1.2.1 Understanding evaluation management process | 4 | 3/2/2023 | 3/2/2023
|  |  | 1.2.2 Identifying user roles and permissions | 2 | 3/2/2023 | 3/2/2023
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 3/2/2023 | 4/2/2023
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 4/2/2023 | 4/2/2023
|  | 1.3 Prepare Documentation | 1.3.1 Prepare Use Case diagram | 2 | 4/2/2023 | 5/2/2023
|  |  | 1.3.2 Prepare ERD diagram | 4 | 5/2/2023 | 5/2/2023
|  |  | 1.3.3 Prepare UI wireframes | 4 | 5/2/2023 | 6/2/2023
|  |  | 1.3.4 Prepare Test Cases | 2 | 6/2/2023 | 6/2/2023
|  |  | 1.3.5 Prepare Data Model | 4 | 6/2/2023 | 7/2/2023
2.0 | Backend Development
|  | 2.1 Set up backend infrastructure | 2.1.1 Configure server environment | 4 | 8/2/2023 | 8/2/2023
|  |  | 2.1.2 Set up database and establish connection | 4 | 8/2/2023 | 8/2/2023
|  | 2.2 Develop User Management | 2.2.1 Implement user registration | 4 | 9/2/2023 | 10/2/2023
|  |  | 2.2.2 Implement user login and authentication | 4 | 10/2/2023 | 11/2/2023
|  |  | 2.2.3 Implement user roles and permissions | 8 | 11/2/2023 | 12/2/2023
|  | 2.3 Develop Evaluation Creation | 2.3.1 Implement form builder for evaluations | 8 | 12/2/2023 | 13/2/2023
|  |  | 2.3.2 Implement evaluation templates | 4 | 13/2/2023 | 13/2/2023
|  |  | 2.3.3 Implement evaluation submission | 8 | 13/2/2023 | 14/2/2023
|  | 2.4 Develop Evaluation Management | 2.4.1 Implement evaluation listing and search | 4 | 14/2/2023 | 14/2/2023
|  |  | 2.4.2 Implement evaluation editing and deletion | 4 | 14/2/2023 | 15/2/2023
|  |  | 2.4.3 Implement evaluation reporting | 8 | 15/2/2023 | 16/2/2023
3.0 | Frontend Development
|  | 3.1 Design UI Mockups | 3.1.1 Create homepage UI | 4 | 17/2/2023 | 17/2/2023
|  |  | 3.1.2 Create evaluation creation UI | 4 | 17/2/2023 | 18/2/2023
|  |  | 3.1.3 Create evaluation management UI | 4 | 18/2/2023 | 18/2/2023
|  | 3.2 Implement frontend functionality | 3.2.1 Integrate API endpoints with frontend | 8 | 19/2/2023 | 20/2/2023
|  |  | 3.2.2 Implement homepage functionality | 4 | 20/2/2023 | 20/2/2023
|  |  | 3.2.3 Implement evaluation creation functionality | 8 | 20/2/2023 | 21/2/2023
|  |  | 3.2.4 Implement evaluation management functionality | 8 | 21/2/2023 | 22/2/2023
4.0 | Testing
|  | 4.1 Perform unit testing | 4.1.1 Test frontend components | 4 | 23/2/2023 | 23/2/2023
|  |  | 4.1.2 Test backend API endpoints | 4 | 23/2/2023 | 23/2/2023
|  | 4.2 Perform integration testing | 4.2.1 Test frontend and backend integration | 8 | 24/2/2023 | 25/2/2023
|  | 4.3 Perform system testing | 4.3.1 Test end-to-end system functionality | 8 | 26/2/2023 | 27/2/2023
|  | 4.4 Perform user acceptance testing | 4.4.1 Collaborate with stakeholders for testing | 8 | 28/2/2023 | 1/3/2023