## Details_break_down(WBS)
| Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date | End Date | Module Total (man-month)
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 1 | 2023-07-03 | 2023-07-03
|  |  | 1.1.2 Develop project schedule | 2 | 2023-07-03 | 2023-07-04
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-07-03 | 2023-07-05
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 1 | 2023-07-03 | 2023-07-06
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-07-04 | 2023-07-07
|  |  | 1.2.3 Understanding Functional Requirements | 1 | 2023-07-04 | 2023-07-04
|  |  | 1.2.4 Identifying Non-Functional Requirements | 2 | 2023-07-04 | 2023-07-04
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-07-04 | 2023-07-04
|  |  | 1.3.2 Prepare UML DFD diagram | 1 | 2023-07-04 | 2023-07-04
|  |  | 1.3.3 Prepare UML ERD diagram | 3 | 2023-07-04 | 2023-07-04
|  |  | 1.3.4 Prepare UML Activity diagram | 2 | 2023-07-05 | 2023-07-05
|  |  | 1.3.5 Prepare UML Class diagram | 2 | 2023-07-05 | 2023-07-05
2 | API Analysis and System Design
|  | 2.1 Analyze API structures and prepare documentation | 2.1.1 Analyze Authentication Authorization API | 2 | 2023-07-05 | 2023-07-05
|  |  | 2.1.2 Analyze Batch Creation API | 2 | 2023-07-05 | 2023-07-05
|  |  | 2.1.3 Analyze Course and Batch Scheduling API | 2 | 2023-07-05 | 2023-07-05
|  |  | 2.1.4 Analyze Assignment API | 2 | 2023-07-05 | 2023-07-05
|  |  | 2.1.5 Analyze Group chat and Classroom API | 2 | 2023-07-05 | 2023-07-05
|  |  | 2.2.1 Prepare documentation about API responses | 4 | 2023-07-06 | 2023-07-06
|  | 2.2 Design User Interface (UI) | 2.2.1 Design home page | 3 | 2023-07-06 | 2023-07-06
|  |  | 2.2.2 Design batch dashboard | 4 | 2023-07-06 | 2023-07-06
|  |  | 2.2.3 Design group chat page | 1 | 2023-07-07 | 2023-07-07
|  |  | 2.2.4 Design classroom page | 2 | 2023-07-07 | 2023-07-07
|  |  | 2.2.5 Design user profile | 1 | 2023-07-07 | 2023-07-07
|  | 2.3 Design database | 2.3.1 Identifying database entities | 3 | 2023-07-07 | 2023-07-07
|  |  | 2.3.2 Analyze relationship between entities | 1 | 2023-07-07 | 2023-07-07
3 | Development
|  | 3.3 Implement Log/Registration Feature | 3.3.1 Write register request and login request models. | 2 | 2023-07-10 | 2023-07-10
|  |  | 3.3.2 Complete register functionality | 6 | 2023-07-11 | 2023-07-11
|  |  | 3.3.3 Complete login functionality | 7 | 2023-07-12 | 2023-07-12
|  | 3.4 Implement Batch Creation and batch creation Feature | 3.4.1 Create model classes | 5 | 2023-07-13 | 2023-07-13
|  | c | 3.4.2 Complete Batch and course creation Feature | 7 | 2023-07-14 | 2023-07-14
|  | 3.5 Assignment and Classroom Feature | 3.5.1 Assignment Creation Feature | 7 | 2023-07-15 | 2023-07-15
|  |  | 3.5.2 Assignment Submission Feature | 5 | 2023-07-16 | 2023-07-16
|  |  | 3.5.3 Classroom Feature completion | 7 | 2023-07-17 | 2023-07-17
|  | 3.6 Implement Chat Feature | 3.6.1 Rearch about chat feature | 2 | 2023-07-18 | 2023-07-18
|  |  | 3.6.2 Implement chat feature | 5 | 2023-07-19 | 2023-07-19
c |  | 3.7 Front end development of authentication, authorization, assignment feature | 3.7.1 Complete login registration pages | 2 | 2023-07-20 | 2023-07-20
|  |  | 3.7.2 Implement assignment pages | 7 | 2023-07-21 | 2023-07-21
| c | 3.8 Front End of chat, classroom feature | 3.8.1 Complete chatroom and classroom pages | 8 | 2023-07-22 | 2023-07-22
4 | Quality Assurance and Project closing
| c | 4.1 Software testing and quality assurance | 4.1.1 Develop test cases | 8 | 2023-07-23 | 2023-07-23
|  |  | 4.1.2 Conduct Unit Testing | 6 | 2023-07-24 | 2023-07-24
|  |  | 4.1.3 Fix bugs and defects | 8 | 2023-07-25 | 2023-07-25
Column1
142