## Details_break_down(WBS)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date | End Date | Module Total (man-month)
Week 1
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-03-07 | 2023-03-07
|  |  | 1.1.2 Develop project schedule | 2 | 2023-03-07 | 2023-03-07
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-03-07 | 2023-03-07
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-04-07 | 2023-04-07
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-04-07 | 2023-04-07
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-05-07 | 2023-05-07
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-05-07 | 2023-05-07
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-06-07 | 2023-06-07
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-06-07 | 2023-06-07
|  |  | 1.3.4 Prepare UML Activity diagram | 2 | 2023-07-07 | 2023-07-07
2 | API Analysis and System Design
|  | 2.1 Analyze API structures and prepare documentation | 2.1.1 Identify the required APIs for the Trainee Selection System module | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.2 Determine the input and output parameters for each API. | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.3 Define the API endpoints and their corresponding HTTP methods . | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.4 Specify the authentication and authorization mechanisms for accessing the APIs | 2 | 2023-11-07 | 2023-11-07
|  |  | 2.1.5 Integrate all API and make it completely functional. | 2 | 2023-11-07 | 2023-11-07
|  |  | 2.2.1 Prepare documentation about API responses | 4 | 2023-11-07 | 2023-11-07
|  | 2.2 Design User Interface (UI) | 2.2.1 Design web pages for applicant registration, job post selection | 8 | 2023-12-07 | 2023-12-07
|  |  | 2.2.2 Design dashboard for admin and applicant | 4 | 2023-12-07 | 2023-12-07
|  |  | 2.2.3 Design file upload mechanism and mailing system | 8 | 13/7/2023 | 13/7/2023
|  |  | 2.2.4 Design interfaces for uploading marks and downloading admit card | 4 | 13/7/2023 | 13/7/2023
|  |  | 2.2.5 Design interface for preparing result for different rounds of selection process. | 4 | 14/7/2023 | 14/7/2023
|  | 2.3 Design database | 2.3.1 Identifying database entities | 8 | 14/7/2023 | 14/7/2023
|  |  | 2.3.2 Analyze relationship between entities | 8 | 14/7/2023 | 14/7/2023
3 | Development
|  | 3.3 Implement applicant registration | 3.3.1 Implement registration form | 2 | 17/7/2023 | 17/7/2023
|  |  | 3.3.2 Develop file upload functionality for photo and CV/resume | 2 | 17/7/2023 | 17/7/2023
|  |  | 3.3.3 Implement job circular management | 2 | 17/7/2023 | 17/7/2023
|  | 3.4 Implement admin approval functionality | 3.4.1 Develop admin panel for viewing applicant information | 2 | 18/7/2023 | 18/7/2023
|  | c | 3.4.2 Implement sorting and filtering options for applicants | 2 | 18/7/2023 | 18/7/2023
|  |  | 3.4.3 Create approval functionality for each job circular | 2 | 18/7/2023 | 18/7/2023
|  | 3.5 Implement Admit Card Generation | 3.5.2 Implement automatic admit card generation | 2 | 19/7/2023 | 19/7/2023
|  |  | 3.5.3 Generate unique serial number/barcode and QR code for identification | 2 | 19/7/2023 | 19/7/2023
|  | 3.6 Implement Exam Tracking | 3.6.1 Develop unique code generation for exam participants | 2 | 20/7/2023 | 20/7/2023
|  |  | 3.6.2 Store generated codes for future reference | 2 | 20/7/2023 | 20/7/2023
|  | 3.7 Implement Marks Upload | 3.7.1 Implement uploading functionality for evaluator marks | 2 | 21/7/2023 | 21/7/2023
c |  |  | 3.7.2 Develop marking categories and criteria | 2 | 21/7/2023 | 21/7/2023
|  | 3.8 Implement Final Selection | 3.7.3 Implement final selection candidate | 2 | 21/7/2023 | 21/7/2023
4 | Quality Assurance and Project closing
| c | 4.1 App testing and quality assurance | 4.1.1 Develop test cases | 8 | 22/7/2023 | 22/7/2023
|  |  | 4.1.2 Conduct system testing | 4 | 22/7/2023 | 22/7/2023
|  |  | 4.1.3 Conduct User Acceptance Testing (UAT) | 8 | 23/7/2023 | 23/7/2023
| c |  | 4.1.4 Fix bugs and defects | 2 | 23/7/2023 | 23/7/2023
|  | 4.2 Project closing | 4.2.1 Revise the project deployment checklist | 4 | 24/7/2023 | 24/7/2023
|  |  | 4.2.2 Deploy the application | 4 | 24/7/2023 | 24/7/2023
2
148