## Details_break_down(WBS)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date | End Date | Module Total (man-month)
Week 1
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-03-07 | 2023-03-07
|  |  | 1.1.2 Develop project schedule | 2 | 2023-03-07 | 2023-03-07
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-03-07 | 2023-03-07
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-04-07 | 2023-04-07
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-04-07 | 2023-04-07
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-04-07 | 2023-05-07
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-05-07 | 2023-06-07
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-06-07 | 2023-06-07
|  |  | 1.3.2 Prepare UML DFD diagram | 4 | 2023-06-07 | 2023-06-07
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-07-07 | 2023-07-07
|  |  | 1.3.4 Prepare UML Activity diagram | 4 | 2023-07-07 | 2023-07-07
2 | API Analysis and System Design
|  | 2.1 Analyze API structures and prepare documentation | 2.1.1 Analyze application API | 4 | 2023-10-07 | 2023-10-07
|  |  | 2.1.2 Analyze applicant API | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.3 Analyze admin API | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.4 Analyze marks upload API | 2 | 2023-11-07 | 2023-11-07
|  |  | 2.1.5 Analyze registration API | 2 | 2023-11-07 | 2023-11-07
|  |  | 2.1.6 Prepare documentation about API responses | 4 | 2023-11-07 | 2023-11-07
|  | 2.2 Design User Interface (UI) | 2.2.1 Design home page | 4 | 2023-12-07 | 2023-12-07
|  |  | 2.2.2 Design applicant page | 4 | 2023-12-07 | 2023-12-07
|  |  | 2.2.3 Design admin page | 6 | 13/7/2023 | 13/7/2023
|  |  | 2.2.4 Design evaluator marks upload page | 2 | 13/7/2023 | 13/7/2023
|  |  | 2.2.5 Design admin marks upload page | 2 | 14/7/2023 | 14/7/2023
|  | 2.3 Design database | 2.3.1 Identifying database entities | 4 | 14/7/2023 | 14/7/2023
|  |  | 2.3.2 Analyze relationship between entities | 2 | 14/7/2023 | 14/7/2023
3 | Development
| c | 3.1 Implement registration functionality | 3.3.1 Receive registration info form the API | 2 | 17/7/2023 | 17/7/2023
|  | 3.2 Implement applicant notice board functionalities | 3.2.1 Show approval of interview | 2 | 17/7/2023 | 17/7/2023
|  |  | 3.2.2 Show notice | 2 | 17/7/2023 | 17/7/2023
|  |  | 3.2.3 Show admit card api ( if approved) | 2 | 17/7/2023 | 17/7/2023
|  | 3.3 Implement admin dashboard functionalities | 3.3.1 Show applicant information for admin | 2 | 18/7/2023 | 18/7/2023
|  | c | 3.3.2 Approve applicant | 2 | 18/7/2023 | 18/7/2023
|  |  | 3.3.3 Assign evaluators | 2 | 18/7/2023 | 18/7/2023
|  |  | 3.3.4 Generate scores | 2 | 18/7/2023 | 18/7/2023
|  |  | 3.3.4 Select final Trainees | 4 | 19/7/2023 | 19/7/2023
|  | 3.4 Implement track applicant functionality | 3.4.1 Implement automated hidden code for exam papers | 2 | 19/7/2023 | 19/7/2023
|  | 3.5 Implement evaluators mark upload functionality | 3.5.1 Implement evaluators mark upload api | 2 | 19/7/2023 | 19/7/2023
|  | 3.6 Implement admit card functionality | 3.6.1 Implement admit card generate api | 4 | 20/7/2023 | 20/7/2023
c |  |  | 3.6.2 Implement admit card download api | 4 | 20/7/2023 | 20/7/2023
|  | 3.7 Implement internal mailing system | 3.7.1 Implement bulk mailing feature | 4 | 21/7/2023 | 21/7/2023
|  |  | 3.7.2 Send bulk mail to coresponds | 4 | 21/7/2023 | 21/7/2023
4 | System testing and Project closing
| c | 4.1 System testing and quality assurance | 4.1.1 Develop test cases | 4 | 24/7/2023 | 24/7/2023
|  |  | 4.1.2 Conduct system testing | 1 | 24/7/2023 | 24/7/2023
|  |  | 4.1.3 Conduct User Acceptance Testing (UAT) | 2 | 24/7/2023 | 24/7/2023
| c |  | 4.1.4 Fix bugs and defects | 1 | 24/7/2023 | 24/7/2023
|  | 4.2 Project closing | 4.2.1 Revise the project deployment checklist | 4 | 25/7/2023 | 25/7/2023
|  |  | 4.2.2 Deploy the system | 4 | 25/7/2023 | 25/7/2023
136