## Details_break_down(WBS)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date (DD/MM/YYYY) | End Date (DD/MM/YYYY) | Module Total (man-month)
Week 1
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-03-07 | 2023-03-07
|  |  | 1.1.2 Develop project schedule | 2 | 2023-03-07 | 2023-03-07
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-03-07 | 2023-03-07
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-04-07 | 2023-04-02
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-04-07 | 2023-04-07
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-04-07 | 2023-05-07
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-05-07 | 2023-05-07
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-05-07 | 2023-05-07
|  |  | 1.3.2 Prepare UML ERD diagram | 4 | 2023-06-07 | 2023-06-07
|  |  | 1.3.3 Prepare UML Activity diagram | 4 | 2023-06-07 | 2023-06-07
|  |  | 1.3.4 Prepare UML Class diagram | 4 | 2023-07-07 | 2023-07-07
2 | API Analysis and System Design
|  | 2.1 Analyze API structures and prepare documentation | 2.1.1 Analyze login and register API | 2 | 2023-07-07 | 2023-07-07
|  |  | 2.1.2 Analyze APIs for batch creation | 2 | 2023-07-07 | 2023-08-07
|  |  | 2.1.3 Analyze APIs for course creation | 2 | 2023-08-07 | 2023-08-07
|  |  | 2.1.4 Analyze batch and course scheduling APIs | 2 | 2023-08-07 | 2023-08-07
|  |  | 2.1.5 Analyze assignment creation API | 2 | 2023-09-07 | 2023-09-07
|  |  | 2.1.6 Analyze classroom API | 2 | 2023-09-07 | 2023-09-07
|  |  | 2.1.7 Analyze classroom post API | 2 | 2023-09-07 | 2023-10-07
|  |  | 2.1.8 Analyze classroom notice API | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.9 Prepare documentation about API responses | 4 | 2023-10-07 | 2023-10-02
|  | 2.2 Design User Interface (UI) | 2.2.1 Design home page | 8 | 2023-11-07 | 2023-11-07
|  |  | 2.2.2 Design login/register page | 4 | 2023-11-07 | 2023-11-07
|  |  | 2.2.3 Design user profile | 8 | 2023-11-07 | 2023-12-07
|  |  | 2.2.4 Design batch and course page | 4 | 2023-12-07 | 2023-12-07
|  |  | 2.2.5 Design assignment creation and submission page | 4 | 2023-12-07 | 2023-12-07
|  |  | 2.2.6 Design classroom page | 4 | 13/7/2023 | 13/7/2023
|  |  | 2.2.7 Design classroom UI for creating post and notice | 4 | 14/7/2023 | 14/7/2023
|  | 2.3 Design database | 2.3.1 Identifying database entities | 8 | 14/7/2023 | 17/7/2023
|  |  | 2.3.2 Analyze relationship between entities | 8 | 17/7/2023 | 17/7/2023
3 | Development
|  | 3.3 Implement login/registration API | 3.3.1 Register trainers and trainees | 2 | 17/7/2023 | 18/7/2023
|  |  | 3.3.2 Authenticate the users into the system | 2 | 18/7/2023 | 18/7/2023
|  |  | 3.3.3 Authorize users to the APIs based on their role | 2 | 18/7/2023 | 19/7/2023
|  | 3.4 Implement batch and course creation API | 3.4.1 Create a batch and set deadline | 2 | 19/7/2023 | 19/7/2023
|  | c | 3.4.2 Assign trainers and trainees to the batch | 2 | 20/7/2023 | 20/7/2023
|  |  | 3.4.3 Create and assign courses to batch | 2 | 20/7/2023 | 20/7/2023
|  | 3.5 Implement assignment APIs | 3.5.1 Create assignment for the trainees | 2 | 20/7/2023 | 21/7/2023
|  |  | 3.5.2 Submit assignment to the trainers | 2 | 21/7/2023 | 21/7/2023
|  |  | 3.5.3 Show assignment submissions | 2 | 21/7/2023 | 21/7/2023
|  | 3.6 Implement classroom features | 3.6.1 Create classroom | 2 | 21/7/2023 | 22/7/2023
|  |  | 3.6.2 Implement post upload and comment feature | 2 | 22/7/2023 | 22/7/2023
|  |  | 3.6.3 Implement notice upload feature | 2 | 22/7/2023 | 23/7/2023
4 | Quality Assurance and Project closing
| c | 4.1 Application testing and quality assurance | 4.1.1 Develop test cases and conduct testing | 8 | 23/7/2023 | 23/7/2023
| c |  | 4.1.2 Fix bugs and defects | 2 | 23/7/2023 | 23/7/2023
|  | 4.2 Project closing | 4.2.1 Deploy application | 4 | 24/7/2023 | 24/7/2023
2
150