## Details_break_down(WBS)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date | End Date | Module Total (man-month)
Week 1
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-07-03 | 2023-07-03
|  |  | 1.1.2 Develop project schedule | 2 | 2023-07-03 | 2023-07-03
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-07-03 | 2023-07-03
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-07-04 | 2023-07-04
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 4 | 2023-07-04 | 2023-07-04
|  |  | 1.2.3 Understanding Functional Requirements | 4 | 2023-07-05 | 2023-07-05
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-07-05 | 2023-07-05
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 4 | 2023-07-06 | 2023-07-06
|  |  | 1.3.2 Prepare UML DFD diagram | 4 | 2023-07-06 | 2023-07-06
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-07-07 | 2023-07-07
|  |  | 1.3.4 Prepare UML Activity diagram | 4 | 2023-07-07 | 2023-07-07
|  |  | 1.3.5 Prepare UML Class diagram | 8 | 2023-07-08 | 2023-07-08
2 | API Analysis and System Design
|  | 2.1 Analyze API structures and prepare documentation | 2.1.1 Analyze application API | 2 | 2023-07-10 | 2023-07-10
|  |  | 2.1.2 Analyze course API | 2 | 2023-07-10 | 2023-07-10
|  |  | 2.1.3 Analyze marks API | 2 | 2023-07-10 | 2023-07-10
|  |  | 2.1.4 Analyze applicant details with search API | 2 | 2023-07-10 | 2023-07-10
|  |  | 2.1.5 Analyze evaluator and marks API | 2 | 2023-07-11 | 2023-07-11
|  |  | 2.2.1 Prepare documentation about API responses | 6 | 2023-07-11 | 2023-07-11
|  | 2.2 Design User Interface (UI) | 2.2.1 Design home page | 8 | 2023-07-12 | 2023-07-12
|  |  | 2.2.2 Design Dashboard page | 8 | 2023-07-13 | 2023-07-13
|  |  | 2.2.3 Design applicant dashbord page | 4 | 2023-07-14 | 2023-07-14
|  |  | 2.2.4 Design filtering page | 4 | 2023-07-14 | 2023-07-14
|  |  | 2.2.5 Design applicants profile and result page | 3 | 2023-07-15 | 2023-07-15
|  | 2.3 Design database | 2.3.1 Identifying database entities | 3 | 2023-07-15 | 2023-07-15
|  |  | 2.3.2 Analyze relationship between entities | 2 | 2023-07-15 | 2023-07-15
3 | Development
c |  | 3.3 Implement job circular with status functionalities | 3.3.1 Crease course or Job circular API | 2 | 2023-07-16 | 2023-07-16
|  |  | 3.3.2 Show multiple course with dates | 2 | 2023-07-16 | 2023-07-16
|  |  | 3.3.3 Connect with froentend for both dashboard | 2 | 2023-07-16 | 2023-07-16
|  | 3.4 Implement application functionality | 3.4.1 Showing multiple courses and apply to individual course | 4 | 2023-07-17 | 2023-07-17
|  |  | 3.4.2 Show application status | 4 | 2023-07-17 | 2023-07-17
|  | 3.5 Implement selection and evaluating functionalities | 3.5.1 Show all applicants | 2 | 2023-07-18 | 2023-07-18
|  |  | 3.5.2 Show filter and select | 2 | 2023-07-18 | 2023-07-18
|  |  | 3.5.3 Show update status and notice | 4 | 2023-07-18 | 2023-07-18
|  | 3.6 Implement marking features | 3.6.1 Implement evaluator add and assign candidate | 2 | 2023-07-19 | 2023-07-19
|  |  | 3.6.2 Add marking with unique id | 2 | 2023-07-19 | 2023-07-19
|  |  | 3.6.3 Update marks of other interviews | 4 | 2023-07-19 | 2023-07-19
|  | 3.7 Implement admit card and mailing feactures | 3.7.1 Develop logic to create admid card | 4 | 2023-07-20 | 2023-07-20
|  |  | 3.7.2 Implement mailing system | 2 | 2023-07-20 | 2023-07-20
|  | 3.8 Implement final selection feature | 3.8.1 Show notification and statua update with froentend | 2 | 2023-07-20 | 2023-07-20
4 | Quality Assurance and Project closing
c |  | 4.1 App testing and quality assurance with frontend | 4.1.1 Develop test cases | 8 | 2023-07-21 | 2023-07-21
|  |  | 4.1.2 Conduct system testing | 4 | 2023-07-22 | 2023-07-22
|  |  | 4.1.3 Conduct User Acceptance Testing (UAT) | 4 | 2023-07-22 | 2023-07-22
|  |  | 4.1.4 Fix bugs and defects | 2 | 2023-07-23 | 2023-07-23
|  | 4.2 Project closing | 4.2.1 Revise the project deployment checklist | 6 | 2023-07-23 | 2023-07-23
|  |  | 4.2.2 Deploy the application and create presentation | 8 | 2023-07-24 | 2023-07-24
2
166