## Sheet1
Week | Task Module | Features To be implemented | Activities to be done | Web Dev (man-day) | Start Date | End Date
1
| Requirement Understanding | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-03-07 | 2023-03-07
|  |  | 1.1.2 Develop project schedule | 2 | 2023-03-07 | 2023-03-07
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-03-07 | 2023-03-07
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-04-07 | 2023-04-07
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-04-07 | 2023-04-07
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-04-07 | 2023-05-07
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-05-07 | 2023-05-07
|  |  | 1.3.2 Prepare UML DFD diagram | 4 | 2023-06-07 | 2023-06-07
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-06-07 | 2023-06-07
|  |  | 1.3.4 Prepare UML Activity diagram | 2 | 2023-07-07 | 2023-07-07
|  |  | 1.3.5 Prepare UML Class diagram | 4 | 2023-07-07 | 2023-07-07
2
| API Analysis and System Design | 2.1 Analyze API structures and prepare documentation | 2.1.1 Analyze total score API | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.2 Analyze evaluation and scoreboard API | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.3 Analyze fixtures API | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.4 Analyze trainee,trainer,admin profile with search API | 2 | 2023-11-07 | 2023-11-07
|  |  | 2.1.5 Analyze match statistics API | 2 | 2023-11-07 | 2023-11-07
|  |  | 2.2.1 Prepare documentation about API responses | 4 | 2023-11-07 | 2023-11-07
|  | 2.2 Design User Interface (UI) | 2.2.2 Design home page | 8 | 2023-12-07 | 2023-12-07
|  |  | 2.2.3 Design mini,mid,final project evaluation page | 8 | 2023-12-07 | 2023-12-07
|  |  | 2.2.4 Design final evaluation page | 4 | 13/7/2023 | 13/7/2023
|  |  | 2.2.5 Design trainee,trainers,admin profile page | 4 | 13/7/2023 | 14/7/2023
|  |  | 2.2.6 Design managers,aptitude and CEO interview evaluation page | 3 | 14/7/2023 | 14/7/2023
|  | 2.3 Design database | 2.3.1 Identifying database entities | 8 | 14/7/2023 | 15/7/2023
|  |  | 2.3.2 Analyze relationship between entities | 8 | 17/7/2023 | 17/7/2023
3
| Development | 3.3 Implement basic functionality | 3.3.1 Receive live marks form the API | 2 | 17/7/2023 | 17/7/2023
|  |  | 3.3.2 Implements login,registration | 3 | 17/7/2023 | 17/7/2023
|  |  | 3.3.2 Show trainee,trainer,admin profile | 2 | 18/7/2023 | 18/7/2023
|  |  | 3.3.3 Implement create batch,assign trainee to batches | 2 | 18/7/2023 | 18/7/2023
|  |  | 3.3.4 Implement Security | 3 | 18/7/2023 | 18/7/2023
|  | 3.4 Implement score and evaluation with scoreboard functionalities | 3.4.1 Show summary of total evaluation system | 2 | 18/7/2023 | 18/7/2023
|  |  | 3.4.2 Show score stats like mini project,mid project,final project,daily task | 2 | 18/7/2023 | 18/7/2023
|  | 3.5 Implement Fixtures functionalities | 3.5.1 Show total marks of the training | 2 | 18/7/2023 | 19/7/2023
|  |  | 3.5.2 Show batch wise trainee and all batch | 2 | 19/7/2023 | 19/7/2023
|  |  | 3.5.3 Show date-wise daily task | 2 | 19/7/2023 | 19/7/2023
|  | 3.6 Implement evaluation system | 3.6.1 Implement daily task creation and submition | 2 | 19/7/2023 | 19/7/2023
|  |  | 3.6.2 Implement quiz system | 3 | 19/7/2023 | 19/7/2023
|  |  | 3.6.3 Implement mini project,mid project,final project | 2 | 19/7/2023 | 19/7/202
|  |  | 3.6.4 Implement managers evaluation,aptitude test and CEO office interview | 2 | 20/7/2023 | 20/7/2023
|  |  | 3.6.5 Show trainee's marks in a row | 2 | 20/7/2023 | 20/7/2023
|  |  | 3.6.6 Show trainee,trainers,admin information, statistics and achievements | 2 | 20/7/2023 | 20/7/2023
|  | 3.7 Implement final score generation | 3.7.1 Develop logic to calculate the serial by their marks | 2 | 21/7/2023 | 21/7/2023
|  |  | 3.7.2 Implement the marks depending on their weitages | 2 | 21/7/2023 | 21/7/2023
|  |  | 3.7.3 Implement final score generation | 3 | 21/7/2023 | 21/7/2023
|  | 3.8 Implement get statistics feature | 3.8.1 Show data like Top trainee and with their marks | 4 | 24/7/2023 | 24/7/2023
|  |  | 3.8.2 Implement commnet system and show in final score generation system | 3 | 24/7/2023 | 24/7/2023
4
| Quality Assurance and Project closing | 4.1 App testing and quality assurance | 4.1.1 Develop test cases | 8 | 25/7/2023 | 25/7/2023
|  |  | 4.1.2 Conduct system testing | 4 | 25/7/2023 | 25/7/2023
|  |  | 4.1.3 Fix bugs and defects | 2 | 25/7/2023 | 26/7/2023
|  | 4.2 Project closing | 4.2.1 Revise the project deployment checklist | 4 | 26/7/2023 | 26/7/2023
|  |  | 4.2.2 Deploy the application | 4 | 26/7/2023 | 26/7/2023