## Sheet1
Work Break Down Structure of Trainee Selection System
Orgnization Name: BJIT Academy
Task ID | Task Module | Features To be implemented | Activities to be done | App Dev (man-hour) | Start Date | End Date | Module Total (man-month)
Week 1
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-03-07 | 2023-03-07
|  |  | 1.1.2 Develop project schedule | 2 | 2023-03-07 | 2023-03-07
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-03-07 | 2023-03-07
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-04-07 | 2023-04-07
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-04-07 | 2023-04-07
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-04-07 | 2023-05-07
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-05-07 | 2023-05-07
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-05-07 | 2023-06-07
|  |  | 1.3.2 Prepare UML DFD diagram | 4 | 2023-06-07 | 2023-06-07
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-06-07 | 2023-07-07
|  |  | 1.3.4 Prepare UML Activity diagram | 2 | 2023-07-07 | 2023-07-07
|  |  | 1.3.5 Prepare UML Class diagram | 4 | 2023-08-07 | 2023-09-07
Week 2
2 | API Design and System Design
|  | 2.1 Analyze API structures and prepare documentation | 2.1.1 Design user related API's | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.2 Design circular related API's | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.3 Design application related API's | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.4 Design approval related API's | 2 | 2023-10-07 | 2023-10-07
|  |  | 2.1.5 Design marks entry related API's | 2 | 2023-11-07 | 2023-11-07
|  |  | 2.1.6 Design applicant related API's | 2 | 2023-11-07 | 2023-11-07
|  |  | 2.1.7 Design admin related API's | 2 | 2023-11-07 | 2023-11-07
|  |  | 2.1.8 Prepare API documentation | 8 | 2023-11-07 | 2023-12-07
|  | 2.2 Design User Interface (UI) | 2.2.1 Design home page | 8 | 13-7-2023 | 13-7-2023
|  |  | 2.2.2 Design circular tab | 4 | 14-7-2023 | 14-7-2023
|  |  | 2.2.3 Design application process & favourite circular tab for applicants | 8 | 14-7-2023 | 15-7-2023
|  |  | 2.2.4 Design notice tab for applicants | 4 | 15-7-2023 | 15-7-2023
|  |  | 2.2.5 Design admin dashboard | 4 | 16-7-2023 | 16-7-2023
|  |  | 2.2.6 Design functionalities related to circular for admin | 8 | 16-7-2023 | 17-7-2023
|  |  | 2.2.7 Design Marks entry interface for both admin and evaluator | 2 | 17-7-2023 | 17-7-2023
|  | 2.3 Design database | 2.3.1 Design databse schema | 2 | 17-7-2023 | 17-7-2023
|  |  | 2.3.2 Analysis of databse schema | 2 | 18-7-2023 | 18-7-2023
Week 3
3 | Development
|  | 3.1 Applicants Registration | 3.1.1 Store the applicant's registration data securely in a database | 2 | 18-7-2023 | 18-7-2023
|  |  | 3.1.2 Implement necessary security measures, such as authentication and authorization | 2 | 18-7-2023 | 18-7-2023
|  |  | 3.1.3 Implement error handling mechanisms to handle any issues that may arise during the registration process | 2 | 18-7-2023 | 18-7-2023
|  | 3.2 Apply for the Desired Circular | 3.2.1 Provide a list of available circulars for applicants to choose from | 2 | 19-7-2023 | 19-7-2023
|  | c | 3.2.2 Create an API to allow applicants to view detailed information about the selected circular | 2 | 19-7-2023 | 19-7-2023
|  |  | 3.2.3 Create an API for applicants to submit their information while applying | 2 | 19-7-2023 | 19-7-2023
|  | 3.3 Approval of Applicants | 3.3.1 Create API's to retrieve and submit review submitted applications from the database | 2 | 19-7-2023 | 19-7-2023
|  |  | 3.3.2 Create API to approve applicants who meet the eligibility criteria for the desired circular | 2 | 20-7-2023 | 20-7-2023
|  |  | 3.3.3 Create API to shortlist candidate for next round | 2 | 20-7-2023 | 20-7-2023
|  | 3.4 Create evaluator | 3.4.1 Store the evalutors data securely in a database | 2 | 20-7-2023 | 20-7-2023
|  |  | 3.4.2 Implement necessary security measures | 1 | 20-7-2023 | 20-7-2023
|  | 3.5 Track Participants of the Written Exams | 3.5.1 Create sytem to generate uid and track participants using that uid | 1 | 20-7-2023 | 20-7-2023
|  | 3.6 Generate Admit Card | 3.6.1 Design Admit Card Mold | 2 | 21-7-2023 | 21-7-2023
|  |  | 3.6.2 Write a sytem to generate QR code & Barcode | 2 | 21-7-2023 | 21-7-2023
|  |  | 3.6.3 Write a sytem to populate the mold & generate the admit card | 2 | 21-7-2023 | 21-7-2023
|  | 3.7 Notification and alert system | 3.7.1 Write an Internal Mailing System to Send Necessary Emails | 2 | 21-7-2023 | 21-7-2023
|  |  | 3.7.2 Write API's for Notice Board | 2 | 22-7-2023 | 22-7-2023
|  | 3.8 Uploading Marks | 3.8.1 Create Marks Upload API for admin | 2 | 22-7-2023 | 22-7-2023
|  |  | 3.8.2 Create Marks Upload API for evaluator | 2 | 22-7-2023 | 22-7-2023
|  | 3.9 Select Final Trainee | 3.9.1 Create API to Select Candiate as trainee | 2 | 22-7-2023 | 22-7-2023
Week 4
4 | Quality Assurance and Project closing
|  | 4.1 App testing and quality assurance | 4.1.1 Develop test cases | 8 | 23-7-2023 | 23-7-2023
|  |  | 4.1.2 Conduct system testing | 4 | 24-7-2023 | 24-7-2023
|  |  | 4.1.3 Conduct User Acceptance Testing (UAT) | 4 | 25-7-2023 | 25-7-2023
|  |  | 4.1.4 Fix bugs and defects | 2 | 25-7-2023 | 25-7-2023
|  | 4.2 Project closing | 4.2.1 Revise the project deployment checklist | 1 | 25-7-2023 | 25-7-2023
|  |  | 4.2.2 Deploy the application | 1 | 25-7-2023 | 25-7-2023