## Details_break_down(WBS)
# | Task Module | Features To be implemented | Activities to be done | App Dev (man-day) | Start Date | End Date | Module Total (man-month)
Week 1
1 | Requirement Understanding
|  | 1.1 Project Planning | 1.1.1 Understanding purpose, scope and objectives | 4 | 2023-07-03 | 2023-07-03
|  |  | 1.1.2 Develop project schedule | 2 | 2023-07-03 | 2023-07-03
|  |  | 1.1.3 Develop a delivery plan | 2 | 2023-07-03 | 2023-07-03
|  | 1.2 Requirements Gathering | 1.2.1 Understanding product perspective, functions | 4 | 2023-07-04 | 2023-07-04
|  |  | 1.2.2 Identifying constraints, assumptions and dependencies | 2 | 2023-07-04 | 2023-07-04
|  |  | 1.2.3 Understanding Functional Requirements | 8 | 2023-07-05 | 2023-07-05
|  |  | 1.2.4 Identifying Non-Functional Requirements | 4 | 2023-07-05 | 2023-07-05
|  | 1.3 Prepare Documentation | 1.3.1 Prepare UML Use Case diagram | 2 | 2023-07-05 | 2023-07-05
|  |  | 1.3.2 Prepare UML DFD diagram | 4 | 2023-07-06 | 2023-07-06
|  |  | 1.3.3 Prepare UML ERD diagram | 4 | 2023-07-06 | 2023-07-07
|  |  | 1.3.4 Prepare UML Activity diagram | 2 | 2023-07-07 | 2023-07-07
|  |  | 1.3.5 Prepare UML Class diagram | 4 | 2023-07-07 | 2023-07-10
2 | API Analysis and System Design
|  | 2.1 Analyze API structures and prepare documentation | 2.1.1 Analyze Authentication API | 2 | 2023-07-10 | 2023-07-10
|  |  | 2.1.2 Analyze Admin API | 8 | 2023-07-10 | 2023-07-10
|  |  | 2.1.3 Analyze Evaluators API | 2 | 2023-07-10 | 2023-07-10
|  |  | 2.1.4 Analyze Dashboard API | 2 | 2023-07-10 | 2023-07-10
|  |  | 2.1.5 Analyze Examinee API | 2 | 2023-07-11 | 2023-07-11
|  |  | 2.1.6 Prepare documentation about API responses | 4 | 2023-07-11 | 2023-07-11
|  | 2.2 Design User Interface (UI) | 2.2.1 Design home page | 8 | 2023-07-11 | 2023-07-12
|  |  | 2.2.2 Design Login Registration page | 4 | 2023-07-12 | 2023-07-13
|  |  | 2.2.3 Design Admin Dashboard | 8 | 2023-07-13 | 2023-07-14
|  |  | 2.2.4 Design Upload Marks page | 4 | 2023-07-14 | 2023-07-14
|  |  | 2.2.5 Design profile pages | 4 | 2023-07-15 | 2023-07-15
|  | 2.3 Design database | 2.3.1 Identifying database entities | 8 | 2023-07-16 | 2023-07-16
|  |  | 2.3.2 Analyze relationship between entities | 8 | 2023-07-17 | 2023-07-17
3 | Development
|  | 3.1 Login Registration | 3.1.1 Login | 2 | 2023-07-18 | 2023-07-18
|  |  | 3.1.2 Registration | 2 | 2023-07-18 | 2023-07-18
|  | 3.2 Course Apply | 3.2.1 Apply for Courses | 2 | 2023-07-18 | 2023-07-18
|  | 3.3 Approval of Applicants | 3.3.1 Approval of Applicants | 2 | 2023-07-18 | 2023-07-18
|  | c | 3.3.2 Filtering Applicants | 2 | 2023-07-19 | 2023-07-19
|  | 3.4 Admit Card Generation | 3.4.1 Admit Card Genetation | 2 | 2023-07-19 | 2023-07-19
|  | 3.5 Track Participants of the Exams | 3.5.1 Hidden Code Generation and Store | 2 | 2023-07-19 | 2023-07-19
|  | 3.6 Upload Written Marks of the Participants | 3.6.1 Assign evaluators for specific answer sheets. | 2 | 2023-07-20 | 2023-07-20
|  |  | 3.6.2 Upload written marks for candidates | 2 | 2023-07-20 | 2023-07-20
|  | 3.7 Mailng System | 3.7.1 Integate maling system | 2 | 2023-07-21 | 2023-07-21
c |  | 3.8 Dashboard | 3.8.1 Generate Dashboard | 2 | 2023-07-21 | 2023-07-21
|  | 3.9 Upload Other Marks | 3.9.1 Upload Other Marks | 2 | 2023-07-21 | 2023-07-21
| c | 3.10 Select Final Trainee List | 3.10.1 Select Final Trainee List | 4 | 2023-07-21 | 2023-07-21
4 | Quality Assurance and Project closing
| c | 4.1 App testing and quality assurance | 4.1.1 Develop test cases | 8 | 2023-07-22 | 2023-07-22
|  |  | 4.1.2 Conduct system testing | 4 | 2023-07-22 | 2023-07-22
|  |  | 4.1.3 Conduct User Acceptance Testing (UAT) | 8 | 2023-07-23 | 2023-07-23
| c |  | 4.1.4 Fix bugs and defects | 2 | 2023-07-24 | 2023-07-24
|  | 4.2 Project closing | 4.2.1 Revise the project deployment checklist | 4 | 2023-07-24 | 2023-07-24
|  |  | 4.2.2 Deploy the application | 4 | 2023-07-24 | 2023-07-24
2
164